## Support Unit Open Cases
(Do Not Modify) Case | (Do Not Modify) Row Checksum | (Do Not Modify) Modified On | Case Type | Case Title | Owner | Customer | Origin | Status | Status Reason | Created On | Initial Estimation Duration | Follow Up Support Team | Age | Priority | Due Date | Actual Duration | Actual Duration (days) | CR #
cbe0782a-af4f-4f67-a273-152118b3117e | g1cTnU/i5r1Co59zmfqjjJIGDliXR30L6w7TW0rPsOfXbUwCTxas+NvQqRILKEtEvB9dDe0jRLg0kaWfugFjcg== | 2026-01-20 12:24 | Development | Utilization Development | Georges Mouaikel | Kurban Group | Change Request | Active | In Progress | 2025-03-24 16:17 | 6 | Yes | 326 | Normal | 2026-01-16 | 112.5 | 14.06
ace33db4-063b-f011-b4cb-7c1e523502d4 | mR2Fy/lF8FWWFTIvlbYiohM6sspmmTf45V1caIk2WUMomJLPiujZdcK4tCWBEPcINLBmP6CxXklAkw77GcAkfg== | 2026-02-12 06:38 | Development | FW: Data Bridge Update for Data transfer to D-365 | Fadi Hanna | Bromine | Change Request | Active | Pending Client Confirmation | 2025-05-27 17:27 | 4 | No | 262 | Normal | 2026-01-23 02:00 | 9 | 1.13
51a548f9-e05b-f011-bec1-7c1e52350f4e | aR28L4FPU7kkovaW33RJ8XdjLlypRrgc4VrvL9MKUTiogNdC52SPxERs2nqWrZYAJz+iDFVNp6HYYGVs/5E7wg== | 2026-01-29 14:05 | Development | Holdal :: Security by Brand | Fadi Hanna | Holdal | Pre-Sales | Active | Pending Client Confirmation | 2025-07-08 12:51 | 32 |  | 220 | Normal | 2026-01-30 02:00 | 120 | 15
c07d0f54-a263-f011-bec2-0022489b52a3 | thBE+hK8mE8FrQD6nR+nGjhnEtRzt3/sJiO5mLPeWk8NjOSOg/Ale3psTbSatkjdAW+z6ZcRIVzXlIdxddwGxw== | 2026-02-11 15:41 | Development | FW: Payment Transfer - issue | Georges Mouaikel | Alfa | Support | Active | Pending Functional | 2025-07-18 09:42 | 4 |  | 210 | Normal | 2025-08-03 09:42 | 1 | 0.13
34a0e263-8a6b-f011-b4cb-7c1e5234c277 | 4zgznP/hyynvwZyVd1uqdRfwjob2Qhav4otb3xxJoOFURZ8Fn1KNk21eR4CwLCbbj2vCBrvsrLNXCPBRk0rnEQ== | 2026-02-11 15:41 | Development | Bromine :: add the manufacturing formula for calculating the RM/PM consumption | Rebecca Estephan | Bromine | Change Request | Active | Pending Customer | 2025-07-28 11:11 | 24 |  | 200 | Normal | 2025-08-13 11:11 | 7 | 0.88
bbff29e8-696c-f011-b4cb-7c1e5234c277 | lO1ATY2xPR0ljncChVqyQSn3tQpUFS+iN/ZuSUZAAAE8iNs/K/gfEAo0aw8DigMTqQ3oyPfUMe/JYkjKE1yJfw== | 2026-01-20 15:42 | Development | alfa :: T157 :: Dev. Image | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2025-07-29 13:51 | 10 | No | 199 | Normal | 2026-01-16 | 0 | 0
9243a03d-726c-f011-b4cb-7c1e52350f4e | 8xIrUp/Tqd2dbsY5C1+lIEAUt/E/RQ3E6VwsmG0OJON4J1ZYtsry9loHJ5RhMUvmqZ8yFwQpt122yLP2eZgPUw== | 2026-01-19 18:08 | Development | alfa :: T103 :: Admin and Knowledge Transfer Sessions | Georges Mouaikel | Alfa | Support | Active | Pending Dev | 2025-07-29 14:51 | 4 |  | 199 | Normal | 2026-01-26 | 0 | 0
55520e0e-c17c-f011-b4cc-7c1e5234c277 | ZbBcyzQP8BIItebKUZHEu40uBo4HMvcipn3XjLDZIOEm6z2R8lmr4cYtKizXHSsodNpV598ZM5sgi029zAcKVA== | 2026-02-04 07:08 | Development | Kurban :: Loan Tracking | Fadi Hanna | Kurban Group | Change Request | Active | Pending Client Confirmation | 2025-08-19 08:55 | 15 | Yes | 178 | Normal | 2026-01-23 02:00 | 131.5 | 16.44
8f5a8a8b-1d7d-f011-b4cb-7c1e52350f4e | EQEAqr+qTQBXRQAXTC5qmMiedgxsQyOxZXj79RVPgN6uQIGu3KxYjuLWLFUIXz9nzuiRUamEe94wFxxlOW+vNQ== | 2026-02-13 06:55 | Development | Fw: MSL and Call Cycles | Fadi Hanna | Holdal | Change Request | Active | Pending Dev | 2025-08-19 19:57 | 4 |  | 178 | Normal | 2026-02-13 02:00 | 49.5 | 6.19
13fcf3f4-897e-f011-b4cc-002248a14dd1 | PN1Gjr8Pc4lp0XJJvSscTi6DqPkcjAJtpQVN2kvmxpCPsOW25CjSvGx9Q8Wu37sT1QKqRUZP8adPDIQVkLAq1A== | 2026-02-11 15:41 | Development | Transfer Order Report- Vensor Security | Jana Sweid | Hawkary | Change Request | Active | Pending Customer | 2025-08-21 15:26 | 24 |  | 176 | Normal | 2025-09-06 15:26 | 11 | 1.38
2da59ef4-5e82-f011-b4cb-7c1e52350f4e | PIwSkvzIROA8d62/fV1WSQDRLwm3lcoKRXM5rUTsInDttaaV71FmoiOlmWFyBllmFXHWq5nHV4V970yehap+CQ== | 2026-01-26 07:45 | Development | FW: GaragePlug Integration | Georges Mouaikel | Kurban Group | Support | Active | Pending Dev | 2025-08-26 12:28 | 4 | Yes | 171 | Normal | 2026-01-21 | 30.5 | 3.81 | 183CRJC9122025
d778e6d9-1284-f011-b4cc-7c1e5234c277 | tzMmeTY6X2FAArnhYEfSIDGkJFkz9mZbo0ITAzRJIldvqlLWCijkAdlwF6z8sEn1iO64TiJrazdHA0iwLIaH2A== | 2026-02-11 15:41 | Development | HRIS Follow-up – Bank Transfers | Georges Mouaikel | Ogero | Pre-Sales | Active | Pending Internal Approval | 2025-08-28 16:28 | 5 |  | 169 | Normal | 2025-09-13 16:28 | 3 | 0.38
f4f44500-1384-f011-b4cb-7c1e52350f4e | 6FcODPOe9nI2nHxTH0EjGqyon1GzWwjjgvKFoaZE0z3GzPjE9awjlGF9bONGSje9fYohQ9SRAgEbf0J6hqXcVA== | 2026-02-11 15:41 | Development | HRIS Follow-up – Pay Slip File | Georges Mouaikel | Ogero | Pre-Sales | Active | Estimation | 2025-08-28 16:29 | 5 |  | 169 | Normal | 2025-09-13 16:29 | 4.5 | 0.56
527b3f4c-3284-f011-b4cc-7c1e52768d60 | AuaGIWvW/iM29i30H2z6Ir+hQxSlFpF0Kb/WcZDXPRxtFZUmxd75hiCibHZ/bbtklw48ZV/0O9iBx/onuL4Jmw== | 2026-02-11 15:41 | Development | FW: CTL and JBC integration | Rebecca Estephan | Bromine | Change Request | Active | Pending Customer | 2025-08-28 20:13 | 24 |  | 169 | Normal | 2025-09-13 20:13 | 9.5 | 1.19
cddbe3ff-918c-f011-b4cc-7c1e52350f4e | QNTh0+wC1LM21M5YGIMhSPSEc5PThFYx4oC3hpqwDz6d8t524Vs/jWO2xq0KReAqpE+xEfny6q586vI76xCAzA== | 2026-02-12 06:57 | Shopify | Fw: Shopify: Purchase Orders and Vendors | Fadi Hanna | Kurban Group | Pre-Sales | Active | In Progress | 2025-09-08 11:59 | 8 |  | 158 | Normal | 2026-02-21 13:28 | 38.5 | 4.81
fd28ea30-fb8e-f011-b4cc-002248a14dd1 | JmgIZPiOWJyhpfvEQVbhr3Got1xw9URDfE/B9bVeNi/4hCM/bq0YW6sSNcpfEsdHVB575Ujgc59brWqG7d0mKQ== | 2026-02-11 15:41 | Development | OpenText integration with ERP | Georges Mouaikel | Etisalat Afghanistan | Support | Active | In Process with Microsoft | 2025-09-11 13:37 | 2 |  | 155 | Normal | 2025-09-27 13:37 | 6 | 0.75
331bad4f-0ce0-4b28-bcb5-2329c2b08796 | HtKbQbBirp4wxh7nf1qD2x+lYkaNfzBl71ou9l7Qc2n2ismJaGwhaqX15ZLdPhMj7pgXj3MgnLLHXaIi+2F+vA== | 2026-02-11 15:41 | Functional Issue | RE: Medical Records - Date issues | Georges Mouaikel | Alfa | Support | Active | Requirement Gathering/Pending Briefing | 2025-09-11 16:21 | 2 |  | 155 | Normal | 2025-09-27 16:21 | 0 | 0
e079ad3e-0a92-f011-b4cc-0022489b52a3 | oWCn3KKYWAEteDx4ZhqoQSvOfl+ZGhcD5nDVuXaYSi2974EPR56K7ckU3M0N4LvIcgzIjSACq4nIoQRqyOagvg== | 2026-02-11 15:41 | New Request | FW: Payment notification to vendors | Georges Mouaikel | Alfa | Pre-Sales | Active | In Progress | 2025-09-15 11:02 | 2 |  | 151 | Normal | 2025-10-01 11:02 | 0 | 0
e32a0bf0-f092-f011-b4cc-7c1e5275c88e | POIKdfBU1ZLfd3Io+Hdzq/hHw3ZxJ0FkyAxeHMEmsszbhyS1rdbXSap/m+6VVAeOsJvMCh+tbHRQi48nfPCIQA== | 2026-02-11 15:41 | Functional Issue | FW: Alert Rules on D365 | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2025-09-16 14:33 | 2 |  | 150 | Normal | 2025-10-02 14:33 | 5.5 | 0.69
82bce95b-5a95-f011-b4cc-7c1e52876976 | BTQuNmklnxKkwsclxhd55rTGvMYHc7+g+eK/SltJ2iA3nWzc+m+2C0f/3cGw9ZA+c/fYgW1Oag0V1EagRq0A+g== | 2026-02-13 07:53 | Development | FW: Meeting Follow - Up / Attendance Templates | Rebecca Estephan | Hugo Boss | Change Request | Active | Pending Dev | 2025-09-19 16:13 | 4 |  | 147 | Normal | 2025-10-05 16:13 | 34.5 | 4.31 | 0176CRJC2122025
f32f6a33-7b97-f011-b4cc-0022489b4ac4 | yBBe+JpVuomzWjrtACc/ABK5Yd2rZguH/tWLk+togSeoxQNlwXPc2cjljGVtbIqDCRkzmz+g29UmE+pc+8exRQ== | 2026-02-11 15:41 | Development | Missing PO Attachments on "Open Vendor Invoices" Screen | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2025-09-22 09:13 | 4 |  | 144 | Normal | 2025-10-08 09:13 | 27.5 | 3.44
f3a49f90-6598-f011-b4cc-7c1e52fac137 | 3Ud70aQlzyRUPwOw1QRCeSMvrsR9z8XLlkg/mB0ynHbPisS9mgB0Pgsj0K+KY69Kd3nL7vFtRFbNWgWs0VRAdw== | 2026-02-11 15:41 | Development | New Role - Logistics team | Georges Mouaikel | Alfa | Pre-Sales | Active | In Progress | 2025-09-23 13:11 | 2 |  | 143 | Normal | 2025-10-09 13:11 | 0 | 0
6247701c-b61d-4803-bd82-64e08ea0893f | 0TT9us3AnkV5FXq+cf567cOg6tb7+clr5FpUkVcSKafKYmQaemm6db06EZK7Gd5EWdpMQFcI+1J+8vVFO+Jbhg== | 2026-02-13 12:59 | Development | Holdal :: Retail Report (Posted/Unposted)l | Rebecca Estephan | Holdal | Change Request | Active | Pending Client Confirmation | 2025-09-26 17:47 | 4 |  | 140 | Normal | 2025-10-12 17:47 | 81 | 10.13
c8d1eca1-aa69-4f30-8ce7-fd2934832b14 | KPYJXsd1h+uQkm2yzQ55Mj4nm8WMXpzcqzfPL8+fwDuhYZ1iW4W+/Dp94t6Jf8RtDJW3xp7pDCnrU/wZi5V/ig== | 2026-02-11 15:41 | Development | Holdal :: Comparative Trial Balance by Month | Jana Sweid | Holdal | Change Request | Active | Pending Client Confirmation | 2025-09-26 17:47 | 24 |  | 140 | Normal | 2025-10-12 17:47 | 19.5 | 2.44
93a48fe1-d09d-f011-bbd3-0022489b4ac4 | SShazNwhFl04khtmopcdI724/7plJuk86z3vu5ZThsdiXsEKHPmGNbfYOVmOnHYJPuD8vb0j30OYxSwLi7NIog== | 2026-02-11 16:01 | Development | FW: Engicon - Reallocation of Salary Cost | Mennatullah El Bahr | Engicon | Change Request | Active | Pending Dev | 2025-09-30 10:42 | 4 | Yes | 136 | High | 2026-01-27 02:00 | 95.5 | 11.94
c404c88c-ed9d-f011-bbd3-0022489b52a3 | fLU+lrBNQaYFHsh2Akr3ZrVYVZVUuQT9cL9wiFg5BEKqaoBZcaJKQVEYR8DPGtH0yMilKYH/0V+GLMAGqe18XA== | 2026-02-11 15:41 | Fixed Assets | Parent Child relationship | Georges Mouaikel | Alfa | Support | Active | In Progress | 2025-09-30 14:07 | 2 |  | 136 | Normal | 2025-10-16 14:07 | 2 | 0.25
a21fd151-ee9d-f011-bbd3-7c1e523502d4 | 6VqNDrtZi9hv8/3urA46vxwSBXwgEI/kdDRADwhQP8BIy517LeiTU9IXY4+64fXrIq+W/CErDmrvIn0s27QG0g== | 2026-02-11 15:43 | Development | Collection by payment method report | Jana Sweid | Holdal | Support | Active | Pending Dev | 2025-09-30 14:12 | 4 |  | 136 | High | 2026-02-13 | 76 | 9.5
a4afada8-5d9f-f011-bbd3-0022489b4ac4 | GotldQC7YR/yyta/xkQbUP3rtk3IeJAkUgi+qtchwjVqxXknyx40UnenokwgeSv5oEMBVzTSnPQWa6h+Xmn7jw== | 2026-02-11 15:41 | Development | AX Reports Issue | Georges Mouaikel | Alfa | Support | Active | In Progress | 2025-10-02 10:02 | 5 |  | 134 | Normal | 2025-10-18 10:02 | 6.5 | 0.81
c97e976e-999f-f011-bbd3-7c1e52876976 | 9be5mdWW4mLdTxkWduoPJz0yTv1Pc349DGwQ6i/xEJzv9tW7lejoLNUaBHgxmXiGHj/zDTcm2/P5qznoEJWV1g== | 2026-02-11 13:59 | Development | FW: Holdal :: Remove Full Order List on POS Inbound Operations | Rebecca Estephan | Holdal | Change Request | Active | Pending Customer | 2025-10-02 17:10 | 24 |  | 134 | Normal | 2025-10-18 17:10 | 10.5 | 1.31
38c7564a-07a5-f011-bbd2-002248a2b399 | fs4sjteOx76s1hHHu07rhI/jsr9cT9WMd1Qh8qJEbnv1tgcchqJmn6woYgm3N6h4FB+3FOZHWDYyvzgh9lDZPw== | 2026-02-11 15:41 | Development | Holdal POS allow edit delete for transfers | Rebecca Estephan | Holdal | Change Request | Active | Pending Dev | 2025-10-09 14:59 | 4 |  | 127 | Normal | 2025-10-25 14:59 | 9.5 | 1.19
d6eca59b-b2a5-f011-bbd2-002248a2b11b | nBnU35Lz/TlAAzzGBzqYEoEqMs9S6nCYv68Cdi942zYu45pt0N6MHcVSZL0x4xBm1w2BvfzaYnviE5qDK7I0qQ== | 2026-02-11 15:41 | Functional Issue | DP Withholding tax | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2025-10-10 11:25 | 4 |  | 126 | Normal | 2025-10-26 11:25 | 0 | 0
5b37c565-001b-4416-8388-dbfb034463ea | QS/1VplA3Uv+WRd/FcmcwMBM2aQykLvDWWyyQ+xGLSj/k2I1YFsZb2QRkPXyoKFUssmkNOS1EBUwevAXCt6LXw== | 2026-01-26 10:44 | Development | Hugo Boss :: WMS Vertical Solution | Fadi Hanna | Hugo Boss | Change Request | Active | Pending Client Confirmation | 2025-10-10 16:38 | 6 | Yes | 126 | Normal | 2026-01-30 02:00 | 78 | 9.75
3e3cc11a-f8a8-f011-bbd3-002248a2bddb | KCB5RPMed5yM0Mbz0q68C8ct8rS2FFFz+qtMTSnN4kpt81KKChLHVbY7OC5+sAQXXhn3nBfbwOpuo/b83n2kXg== | 2026-02-11 15:41 | Development | AX Reports Issue #2 | Georges Mouaikel | Alfa | Support | Active | In Progress | 2025-10-14 15:20 | 5 |  | 122 | Normal | 2025-10-30 15:20 | 0 | 0
0faf77ca-daa9-f011-bbd3-002248a2b3c0 | H+Yl6Dm+DWw2cEc+0o+34XEXYTTthsglGxjA8xZJmpacQqE5NIS3cf2ayNm+Eh1HG8eAUGnutlrWNdYTzJaRRg== | 2026-02-11 15:41 | PowerBi | Kurban :: Profitability by Car | Fadi Hanna | Kurban Group | Change Request | Active | Pending CR | 2025-10-15 18:23 | 6 |  | 121 | Normal | 2025-10-31 18:23 | 1.5 | 0.19
239eb983-8aae-f011-bbd3-002248a2bddb | eJ2liB4heSBsVAndBxZBaI22x0nEoote9+KRIhJIW86HLBrILKBcAfyqr2tBklPJSz5BQZqtSJxb45/X1RcqAQ== | 2026-02-11 15:41 | Technical Issue | Fw: ERPD365 SID change | Georges Mouaikel | Alfa | Support | Active | In Process with Microsoft | 2025-10-21 17:31 | 24 |  | 115 | Normal | 2025-11-06 17:31 | 0 | 0
c7be9468-2baf-f011-bbd3-002248a2bddb | lZDjtBBKyKeI6ovUNOnLIx2RdDyFvRpaCzDSqmAyC0xUSitcGfP3T/Da8eI0tXk/cRcwZHDdF25aSC62t/kIkQ== | 2026-02-11 15:41 | Development | Free text invoices layout | Georges Mouaikel | Alfa | Pre-Sales | Active | Pending Client Confirmation | 2025-10-22 12:43 | 4 |  | 114 | Normal | 2025-11-07 12:43 | 1 | 0.13
0e2961f0-49af-f011-bbd3-002248a2b11b | wcPs2GoufVXvoiLWWVHCefhLXkXirZuG4F556koKL841/bp18MwrYZ4QsbUfohQPZHpKCrCr4fR1vWURgHOVqg== | 2026-02-12 06:57 | Development | FW: Query Sellout | Fadi Hanna | Hugo Boss | Change Request | Active | In Progress | 2025-10-22 16:21 | 40 | Yes | 114 | Normal | 2026-02-21 13:28 | 12.5 | 1.56
3f5bf493-09b0-f011-bbd3-002248a2b75e | WVvSJvgh1ku+f3Nb/uay7tZPYi4RVRn73VvHV7yA/4+Bibi2KvmQGx0WGRiWYobCkq3ajUShwqbPjPrg2UpWgQ== | 2026-02-11 15:41 | Development | Unable To Extract "Asset Inventory Acquisition Report" | Georges Mouaikel | Alfa | Support | Active | Pending Dev | 2025-10-23 15:13 | 4 |  | 113 | Normal | 2025-11-08 15:13 | 17 | 2.13
783c97a0-1cb0-f011-bbd3-002248a2bddb | gr9iy38HIyTbRR7IXLrO0bIGcbscUV3+H9qjVplZ/gQ/gX95uyMvdmbN+Emo5o9CkAtu5XDGNpllXm/ioeM8Dg== | 2026-02-11 13:54 | Development | FW: Update in the WMS Integration | Rebecca Estephan | Holdal | Change Request | Active | Pending Client Confirmation | 2025-10-23 17:29 | 24 | Yes | 113 | Normal | 2025-11-08 17:29 | 6 | 0.75
58cd84f8-02b3-f011-bbd2-7ced8d71b5a4 | FiK6S2fB71mGUIxEOc6ZQ8BC0ITxoKUOD8c6rKqO+H4EavDNCZ4oMsRLo3FZMI/ZCzoV/9sNMwtnLhq/iaiApA== | 2026-02-11 15:41 | Development | FW: Modifications on MIR Process on D365 by Activation the Device Role | Rebecca Estephan | Bromine | Change Request | Active | Pending Customer | 2025-10-27 09:03 | 24 |  | 109 | Normal | 2025-11-12 09:03 | 19 | 2.38
fbdf0073-26b6-f011-bbd3-002248a2b11b | hjaGx8wP7WTGEyxWhIlOiMr/6ZG+mCg5zZwL2zG4+bzGivV4HJSZ6lJz2jClAtP/fDJFKJmOpyR5JoToG0Midw== | 2026-02-11 15:41 | Development | Disabling out of stock quantity sales in stores | Rebecca Estephan | Holdal | Change Request | Active | Pending Customer | 2025-10-31 08:55 | 24 |  | 105 | Normal | 2025-11-16 08:55 | 3 | 0.38
55e2edde-c6b8-f011-bbd3-002248a2b3c0 | Ftwb1DleR/M8hsDPh/4xUazjxmX2xfxQl0kV5m9s/5hKyg4qoXcwJ+WfsbFADWuSidkAGq8CL0wVgRrLCwHOlQ== | 2026-02-05 11:06 | New Request | FW: Engicon Intercompany Requirements | Mennatullah El Bahr | Engicon | Pre-Sales | Active | In Progress | 2025-11-03 17:08 | 2 |  | 102 | Normal | 2026-01-31 02:00 | 5.5 | 0.69
f7ab5457-02bb-f011-bbd2-002248a2b399 | QkFLv6k/uByxYP5cEjIBMzVQ0LEGT4dtb2U1EDIb/AvLHqi0Cuefn3oxHK+IWzEJ6iS+wnAW51PWmDCF9QCzrg== | 2026-02-11 15:41 | Development | FW: Deferral run Oct-25 | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2025-11-06 13:19 | 4 |  | 99 | Normal | 2025-11-22 13:19 | 13.5 | 1.69
3a448286-a62d-45ba-96e0-6913e003a24f | NlxBnxC4zjbH7ns1wdU7HdrKJmHLQyYIAkyFBqkK2YyIa7V0rLVC6gQV9MTTc30KklfNk6Kz6ZxnyTd4KsEtlA== | 2026-02-11 15:42 | R&D | R&D :: Unified Pricing Management | Jana Sweid | Info-sys | Internal Support | Active | Researching | 2025-11-10 11:28 | 16 |  | 95 | Low | 2025-12-10 11:28 | 10 | 1.25
032b8030-5710-4fcb-a0a2-738b17530c6b | D6/5olTcawdUWYxvIqRSQPAUoUTmi+iC9V0DjG6/CxvLlHD38o7+q1WmvALQy7e14XWyGnTz/ZYzCKaGPkMs/w== | 2026-02-11 15:42 | R&D | R&D :: Business Performance Analytics (BPA) | Jana Sweid | Info-sys | Internal Support | Active | Researching | 2025-11-10 11:34 | 60 |  | 95 | Low | 2025-12-10 11:34 | 0 | 0
75f0e691-82c0-f011-bbd3-002248a2b75e | e3XhJooffyljiTauPRl1pRdFH00pdQuYem0BQnauxUBWzrnLLirWekPRhkBciRVxj9D3EM/AY9d16PcnwP9kmg== | 2026-02-11 15:41 | Development | Extracting Voucher transactions and session timeout on D365 | Georges Mouaikel | Alfa | Support | Active | Pending Dev | 2025-11-13 13:19 | 4 |  | 92 | Normal | 2025-11-29 13:19 | 5.5 | 0.69
6df8d95b-a982-4578-bda9-d1e8de8fb5ab | GIkEQyd6dcxH5QrO9BYUTRhEnzsWf8kJ7giTJM09LPbftWoQ6lRec6pXs5n/lX5Qkbk6zam6r6L7ieA6xzfe5A== | 2026-02-11 15:42 | Training | Retail Training | Rebecca Estephan | Info-sys | Internal Support | Active | In Progress | 2025-11-14 09:06 | 64 |  | 91 | Low | 2025-12-14 09:06 | 0 | 0
6bdc25b9-5132-4836-866b-206c89875819 | gsH8lBXYo/1Y3nxehdYvcjRaQPkL2rUoSptBGrBrfxMj3XlUGK5GRuI/QXaMdCQe0OcKcj7XFkpdyWxtz3C8ZA== | 2026-02-11 15:42 | Retail & POS | Retail Training | Jana Sweid | Info-sys | Internal Support | Active | Researching | 2025-11-14 09:09 | 64 |  | 91 | Low | 2025-12-14 09:09 | 0 | 0
ed38dbec-9fc3-f011-bbd3-002248a2b75e | j2YWroGgoHYPFfqgaWtiqUpAgsw/F6PvwTGwvyW9tuO7+z1+emmTlgRkgoQJcK13WK/CrvI4SQzvQ1sVClThTQ== | 2026-02-11 15:41 | Development | Payroll Interface | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2025-11-17 12:27 | 4 |  | 88 | Normal | 2025-12-03 12:27 | 1.5 | 0.19
dace8a93-afc3-f011-bbd3-7ced8d71b5a4 | x4cOAWwdLEKms4eALpwIQKHglOsVUgKyXf/dLNtGmtZiI4P+VjnLfLb8yDd/QRSNAu+XDlGyHLGTN6eyEEetMw== | 2026-02-11 15:41 | Development | Dealer Prepaid Report Calculation Error | Georges Mouaikel | Alfa | Support | Active | Pending Dev | 2025-11-17 14:19 | 4 |  | 88 | Normal | 2025-12-03 14:19 | 0 | 0
99532b89-60c4-f011-bbd3-002248a2b3c0 | 8HHiEDyriLkqAyyqHoMqUTYn9zDwim3+nY3sC0LlAyxxfAcajgs1EauKBEz3wFYT/jKA6ImISceFJIPagP8qIw== | 2026-02-11 15:41 | Development | SH Date On Label | Jana Sweid | Second House | Support | Active | In Progress | 2025-11-18 11:26 | 4 |  | 87 | Normal | 2025-12-04 11:26 | 12.5 | 1.56
22a354b3-60c4-f011-bbd3-7ced8d71b5a4 | ABtqA5T+997/pOCZmLDzEns4a+iivIZsXtyxgaB0O20XUNMJ7f32yjspmSkrxdZsC0lchZ9zHDDUXroJqXTlIA== | 2026-02-11 15:41 | Development | SH Add name of MR on Transaction screen Dea | Jana Sweid | Second House | Pre-Sales | Active | Pending Customer | 2025-11-18 11:27 | 4 |  | 87 | Normal | 2025-12-04 11:27 | 8 | 1
446e4918-ecc5-f011-bbd3-002248a2b75e | kO5W1Do/9ruHm/R2lmEhTgs3uGaPLLYGo+Ww52Poa3k9lYFynlv5XENzd84OlVO94IXIgfFZOJh65ufQEOOscQ== | 2026-01-26 10:40 | Development | FW: Actual Cost Report/difference between the report and the GL TB | Rebecca Estephan | Bromine | Support | Active | In Progress | 2025-11-20 10:37 | 4 |  | 85 | Normal | 2026-01-30 | 2.5 | 0.31
4929db74-f9dc-41b0-80ae-6684f2d56dcb | CDdML+8kcLD1d3yN8PNLUVwVbCvAzVrdWe2//o2bXTQN9JzHKnHIgALeZKwQK8DnjfPaPGs5JGVSeTu/Ra6jog== | 2026-02-11 15:41 | Development | FW: Error Exporting "Adjustment Per Department" Report | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2025-11-27 11:29 | 4 |  | 78 | Normal | 2025-12-13 11:29 | 19 | 2.38
4ba2d9b4-fc8e-4b04-9706-ba0e7f9936ae | vQdxjVsEN4Do/h6omMspndwDf/EBKRJtC+gwS+5ZtnlLjslhM7BWqXWkF1rZ/4q64uerF91knHkH50FrwCXHjQ== | 2026-02-11 15:41 | Development | RE: Solution Design for Review | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2025-11-27 11:44 | 4 |  | 78 | Normal | 2025-12-13 11:44 | 1 | 0.13
70a8eff5-9ccb-f011-bbd3-002248a2bddb | GMgjGJ+lvgcORC0N4YQCRe1iLzyzNqtcrZNvV+ATL9bjYv46Q3HjnSiqmvWeJxOml82yMZTppBCvmE2EKBa0dA== | 2026-02-11 14:18 | Development | FW: Request: Add "Season" Field to List of Product Report | Jana Sweid | Holdal | Change Request | Active | Pending Client Confirmation | 2025-11-27 16:26 | 4 | No | 78 | Normal | 2025-12-13 16:26 | 34.5 | 4.31
4ff2ebb7-61cc-f011-bbd3-002248a2b11b | tPt/bGdB7qB2sIeNQzbFYWnA+tEKsCBpV4Tqdqe4bMVWmSWUKhXT4pPBnINJ+9FGhQsR2ufakhYovIIWY4/ujw== | 2026-02-11 15:41 | Development | Holdal :: Customer Attributes Parameterization | Rebecca Estephan | Holdal | Change Request | Active | Pending Customer | 2025-11-28 15:54 | 24 |  | 77 | Normal | 2025-12-14 15:54 | 2.5 | 0.31
a76c07ed-cace-f011-bbd3-002248a2bddb | D6x1HVUq/Im+17xI2qoNYuBvyfeytUXzSikmencR5gbyAHwMfcmm6nDIC4fGlirzIqqRIpoCHXMHQsRg+9POzg== | 2026-02-13 07:40 | Development | FW: Import Tool without Size, color and Season | Jana Sweid | Hugo Boss | Support | Active | Pending Dev | 2025-12-01 17:32 | 4 |  | 74 | Normal | 2025-12-17 17:32 | 27 | 3.38
45646e75-a93e-4209-97de-96707e68b80d | InyGrcSlntuXcTgt1G54llmqzBZzTA85sFsa5sR6E8BF98jRRil+GetiKKecJUJywrXY6FaOxGV9D8nPEstbqg== | 2026-02-11 15:42 | Training | Retail Training Practice | Mennatullah El Bahr | Info-sys | Internal Support | Active | In Progress | 2025-12-02 09:23 | 32 |  | 73 | Low | 2026-01-01 09:23 | 31 | 3.88
c82df185-6bcf-f011-bbd2-002248a2b399 | hY1OBooRWtmhzGNUjxLNf2zymz+1ztFYjV8JKQcH03HOuZ8hJgwaugOqVoyTsYkzLniRDxFaqr7K6DVy4Z90Eg== | 2026-01-30 13:16 | Development | Project Invoice Template Modification for Multi-Subproject Invoicing (KSA Legal Entity) | Jana Sweid | Acuative | Change Request | Active | Pending Dev | 2025-12-02 12:42 | 4 |  | 73 | Normal | 2026-01-30 | 31 | 3.88 | 0186CRJC22122025
a48dc184-3ed0-f011-bbd3-002248a2b38f | LtFs1Xk8cEy4/Du+dm+zt202HnUy//b20ooiCHvHY8kmFV/gxxiYTS5SG4F/x0o6RXxMcyvXjOObJfwO6BD6Tw== | 2026-02-11 15:41 | Development | Partial reception | Georges Mouaikel | Alfa | Pre-Sales | Active | Not Started | 2025-12-03 13:52 | 4 |  | 72 | Normal | 2025-12-19 13:52 | 2 | 0.25
4129e5be-d3d4-f011-8544-002248a2b3c0 | 4haPLosJEonw91NI+deFaflXi9qUYJOWalff6tjK/35mJi0LCH8Fie9XzVfa9lg/fkqFo3oygUKk6ipLA+miUA== | 2026-02-11 15:41 | Development | QO Fail Notification | Rebecca Estephan | Bromine | Change Request | Active | Pending Customer | 2025-12-09 09:51 | 10 |  | 66 | Normal | 2025-12-25 09:51 | 2 | 0.25
e85b51d4-d6d5-f011-8543-002248a2b399 | I8IVziFBgrRBVtvFwtvgWlOyJwzaY1dUHznOda48bzO1Q35OrO25wSwILza3AofmO9Mz8tIGsi4kQbtlYuvZ6Q== | 2026-02-11 15:41 | Development | FW: D365 Final Product Lab Results and BLISS workflow | Rebecca Estephan | Bromine | Change Request | Active | Pending Dev | 2025-12-10 16:45 | 4 | No | 65 | Normal | 2025-12-26 16:45 | 27.5 | 3.44
181b3ebc-8dd6-f011-8544-7ced8d71b5a4 | uCEDAmgEVmKZ7Kgs2mKzPHV87bWIoN98GjpbidcEI+NL9X5nA8Qa6NEPN5wsO8u1tlJ6mmvHuInaPf9EFYedtA== | 2026-02-11 15:41 | Development | Feasibility on contract Management | Georges Mouaikel | Alfa | Pre-Sales | Active | Not Started | 2025-12-11 14:35 | 5 | No | 64 | Normal | 2025-12-27 14:35 | 0 | 0
0e5a5164-8ad9-f011-8544-002248a2b3c0 | hkprIOoxfwGUmWzrE2eZh06JTbIt94l5LKaeBuOhOUxZdMkQtKt9MpDtwPuuy1dJnf+xBU+1hjMuRpPCBCBYDA== | 2026-02-13 13:02 | Development | FW: Request to Initiate New ERP Project for Logistics & Packaging | Rebecca Estephan | Bromine | Change Request | Active | Estimation | 2025-12-15 09:48 | 10 | No | 60 | Normal | 2025-12-31 09:48 | 4.5 | 0.56
7d52132e-98d9-f011-8544-002248a2b3c0 | HR63jvAji4i2N9NWnt2JZmw6pGFZ7R5RkUaOskoIU8ks+fWp6KmjbpfmeKow9/loJT45u82dBtclOAnqLAnGsw== | 2026-02-11 15:41 | Development | FW: Customer Account Statement | Mennatullah El Bahr | Engicon | Support | Active | Pending Dev | 2025-12-15 11:27 | 4 | No | 60 | Normal | 2025-12-31 11:27 | 21 | 2.63
205122fc-a3d9-f011-8544-002248a2bddb | 4Zkz9Lvk1MxOeYf3wPmurs6hlVX7ZcUGyVpbO6sus9rwPjOqeFVukje3pcPhvQR0l+FiQERJBkJoATyDBGgQvw== | 2026-02-10 10:49 | R&D | Feature Management :: Retail and Commerce | Rebecca Estephan | Info-sys | Support | Active | In Progress | 2025-12-15 12:51 | 24 | No | 60 | Low | 2026-03-31 | 5 | 0.63
596d8afb-65eb-4e9c-ada6-9ba8fb72d4be | soxNLMZPh0/5fHEw6ZQLVNggyNvHDkyh3UytvxuGq3wwn3CNxWBKIhhqtWxZJYVY+mWo9EvBBba17D+otsY8gQ== | 2026-02-10 10:50 | R&D | Feature Management :: Retail and Commerce | Mennatullah El Bahr | Info-sys | Support | Active | In Progress | 2025-12-15 12:55 | 24 | No | 60 | Low | 2026-03-31 | 34.5 | 4.31
ac9cbaf2-2715-4bf0-8e67-f39357550d1f | mzXQDN/5M0E0h61B0rmW6Kw4ocEUH7/xa7jFcZs5EZV5odDXDZJIDb6DsMEppiB0+/PbBXGpcdWCmI4h2K5dYA== | 2026-02-02 06:36 | R&D | Feature Management :: Retail and Commerce | Jana Sweid | Info-sys | Support | Active | Researching | 2025-12-15 12:58 | 24 | No | 60 | Normal | 2026-03-31 | 11.5 | 1.44
50086fe6-a7d9-f011-8544-002248a2b3c0 | plhMv0tyV7Z3uao/hfn4XhwiM94UygGxqOO/BFkajl9e5WxRWGZTjf03qCVCNxbaIaJB12P57XxfT+Qv9cdNSQ== | 2026-02-12 06:57 | Reconciliation | Credit Limit Calculation | Fadi Hanna | Holdal | Support | Active | In Progress | 2025-12-15 13:19 | 10 | No | 60 | Normal | 2026-02-20 13:19 | 12 | 1.5
c035ac4e-b0d9-f011-8544-002248a2b75e | ZWCA4CLB0Ee1vE9HuJHypBYJyiL3iI8Sa/I8eE6MZ5aNozC0FJDEJSO9ObKf09TJchM6pk4Oeg+Yg9KOl2aI2Q== | 2026-02-11 15:41 | Development | Etisalat :: Environment Version Issue | Fadi Hanna | Etisalat | Support | Active | Pending Client Confirmation | 2025-12-15 14:20 | 4 | Yes | 60 | Normal | 2025-12-31 14:20 | 0 | 0
c978b4be-b057-458d-8e14-7c24b16a6ce6 | 5C6i3pHOztTzobgPjj2BKZfzU64hDnAcezT+2DaOK2CwrjdV37cTwud5UfV7YEHq+ZgaBY0nImY79pGkS68oLQ== | 2026-02-10 10:40 | Training | Training :: Budget Module | Mennatullah El Bahr | Info-sys | Internal Support | Active | In Progress | 2025-12-16 14:49 | 75 | No | 59 | Low | 2026-03-31 | 7 | 0.88
a5c0d224-0dc1-4a5a-8389-fe6bbbc5079c | omnE3mpGPlBwbWw1WLHS1akzpiVLjxVxJH8Ph7BVoScGEpZVWALIHy+MO4GGEMO1Xq0T5LsLktuWXy9MrDyUaw== | 2025-12-17 13:25 | Development | Preparation: AI-Driven Demand Forecasting in Dynamics 365 F&O | Mennatullah El Bahr | Info-sys | Change Request | Active | Not Started | 2025-12-17 15:22 | 112 | No | 58 | Normal | 2026-06-30 | 0 | 0
1fdb16a8-a95e-45ae-992b-26f7d969b297 | WEJ3VL3+Hl5Fs6INfN0RZ5rjbn+fQlGmP/QTeLLaP8V+CziYiDKcUlkp/99iKxatFodBmVAtqOCAH/HEu8fprA== | 2026-02-11 15:41 | Development | Holdal Coupon Usage Limit Across Legal Entities | Rebecca Estephan | Holdal | Change Request | Active | Pending Customer | 2025-12-17 16:21 | 24 | No | 58 | Normal | 2026-01-02 16:21 | 10.5 | 1.31
a1d6fde6-5edb-f011-8544-002248a2b75e | wvG6m8BNApgd1xxi8K9CuP261AuMAVV7tY7I0KCoQLftV7EC5/giG5tz22oc2zrLsIJBjg51h8Zq2yrpScg58Q== | 2026-02-13 07:23 | Development | Engicon :: Zatka Production Env Setup | Mennatullah El Bahr | Engicon | Support | Active | Pending Dev | 2025-12-17 17:42 | 4 | Yes | 58 | Normal | 2026-01-02 17:42 | 7.5 | 0.94
f6cf2c89-0bdf-f011-8544-002248a2b11b | 4SpSJ2PtFr+QnejND+t1aZvkS6tXZK6US0znj9Sm3eBfcEejGoqd38WQ/fyzaNB4Gyt7PqVbaLFENwC9UN0FXg== | 2026-02-11 15:41 | Development | Second house :: Invoice layout Case | Jana Sweid | Second House | Support | Active | Pending Dev | 2025-12-22 09:55 | 4 | No | 53 | Normal | 2026-01-07 09:55 | 21.5 | 2.69
cd7e669c-a94b-455a-8633-d581f6157850 | FdbuyouwnKeKHBxbq7fhEBIAWh6eHFGVuKrV8UWoUFF3heW2182hYvr89ZcIR6kitcyhIprnd/KjeZKobsjHzw== | 2025-12-26 09:34 | New Request | GnTech :: Analysis & Solution Design :: FRD | Abdo Khoury | GnTech | Project | Active | Not Started | 2025-12-26 10:39 | 56 | No | 49 | Normal | 2026-03-11 | 0 | 0
ea7362db-1d1c-4cd2-a36a-2b4053831992 | PGy637+/W5ptavMm8sh/5QDLyq4JiwaBWcZwz4jT7EAzqkFBEkyzZNknElgGjwiLQFSqKxd1vvu+9bhG6RiN9w== | 2025-12-26 09:39 | New Request | GnTech :: Setup + POC + Training | Abdo Khoury | GnTech | Project | Active | Not Started | 2025-12-26 10:46 | 136 | No | 49 | Normal | 2026-04-06 | 0 | 0
1d50ef12-413a-42cb-ac88-e0afbef7fb45 | 2eWRAeo8F6K19+idpsU2DlK77lXDvqGdMLkM0c9qftue6VMAOJ4p8/3fbyVcRVN+MmeppRhOsGC1DYsPkTtovw== | 2025-12-26 09:39 | New Request | GnTech :: UAT | Abdo Khoury | GnTech | Project | Active | Not Started | 2025-12-26 10:49 | 64 | No | 49 | Normal | 2026-04-16 | 0 | 0
232be6d2-2597-4496-a3a5-236085d4a90c | QBpDLtyGOMSu14pRGPpc247I7c9LIYAl6q/A81PZwkm3CPlJwlNdKR/hPz9b+i+8RFJLLCMWnaaZdHB+D7u/KQ== | 2025-12-26 09:40 | New Request | GnTech :: Production Env Setup & Go-Live | Abdo Khoury | GnTech | Project | Active | Not Started | 2025-12-26 10:51 | 64 | No | 49 | Normal | 2026-04-28 | 0 | 0
20154013-8be4-f011-8543-002248a2bddb | x1NPN4MmYfOpfun/tEULTt7pHc0hukgdy1vjUkALiQa2/GVyYpDcYH1F+cXZDk4QbNJ3jPPIK5g5IilQgdClZg== | 2026-02-13 07:08 | Development | GRAY MACKENZIE -APPLY- | Jana Sweid | Holdal | Support | Active | In Process with Microsoft | 2025-12-29 09:51 | 22 | No | 46 | Normal | 2026-01-14 09:51 | 16.5 | 2.06
c76dd331-91e4-f011-8544-002248a2b11b | l7YpWOxutZKCv98Eia9YxoHIhcMMzRbf1h4pLsE0VhGwQg7kvKNc3NE+hszRXv/xRipb0KE/pu28jrSOh22qQA== | 2026-02-11 15:41 | Budget | Submitting issue | Georges Mouaikel | Alfa | Support | Active | Not Started | 2025-12-29 10:35 | 3 | No | 46 | Normal | 2026-01-14 10:35 | 0 | 0
354580e3-4fe5-f011-8544-002248a2b11b | 2j2k/ApVO20dzuEbhdF1hYFtoN4nXuKvGyfMzm/32Q7JaEuuC+Ijllpak2EwaWlJ6hDrkXx5fff/tY6WM5YUEQ== | 2026-01-01 12:09 | New Request | On-Premise Deploy Package Ste | Georges Mouaikel | Info-sys | Support | Active | Not Started | 2025-12-30 09:20 | 1 | No | 45 | Normal | 2026-01-05 | 0 | 0
edeb9bd6-aee7-f011-8544-002248a2b11b | Fxxc6MuSVFmioScf7628L9zmX1raQA55ep674TCUu5cRRC3Nbx90UF/BTQAY+ZxZbhDlfLELb1giuA/n3+YP4Q== | 2026-02-05 11:02 | Migration | Engicon :: GL Opening Balances Migration – 01/01/2026 | Mennatullah El Bahr | Engicon | Project | Active | Not Started | 2026-01-02 09:44 | 20 | Yes | 42 | High | 2026-01-30 | 5 | 0.63
c06dd235-9f22-4dc5-8cb8-168f73ed4b31 | sxqQHxuSJKPmbLvG+I6N/2soxagbjpftCHMsQUhHZrUIrk6XvP/R8LDrJSvgI4kcYzdGTrQKnuWX9bQeWciQGQ== | 2026-02-11 15:41 | Development | RE: D365 - 3DS integration | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2026-01-05 12:35 | 4 | No | 39 | Normal | 2026-01-21 12:35 | 3 | 0.38
75bae4fb-15ec-f011-8543-002248a2b399 | 91QUzmxI6C/sGRM2Bk+Cea+cLeyHUnDOmcnGp9vNLnBxpY8hnael9bHB2lGRmDHRDblPfY6K4uRQDkzko6uJTg== | 2026-02-11 15:41 | New Request | P&L Template | Abdo Khoury | Hugo Boss | Support | Active | Not Started | 2026-01-08 00:13 | 10 | No | 37 | Normal | 2026-01-24 00:13 | 0 | 0
3ea31ca1-20c2-4477-a5b7-3c9c7fcc22f1 | MMWYL903ug4w4r8nHJ7vcPT8GE3zH4qaNM7B9Ss/vR945MfOt0tFPmoeq5mE7kHG7VRdqODsvHxIiiowIk7+Uw== | 2026-02-11 15:41 | Development | FW: Show Payment Many Report | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2026-01-08 09:21 | 5 | No | 36 | Normal | 2026-01-24 09:21 | 17 | 2.13
95a64476-78ec-f011-8544-002248a2b124 | ttTnO62IoEAIPk/6aI4mL79dsQpGC2a75iG/PQrxJnb82+8seE9Qu4ojDJ+5I3/NcVBNvLaZFYIEwaf4jHEeyg== | 2026-01-26 07:44 | Development | FW: Wizard Migration | Georges Mouaikel | Kurban Group | Support | Active | Not Started | 2026-01-08 11:58 | 8 | No | 36 | Normal | 2026-01-31 | 32 | 4
c93a0750-9fec-f011-8544-002248a2b75e | 75rfBMHsPPKqetk9WlHAWETHD153ueOKayB29hzYg4eO7LYgdzGiz3IAbD3y55LUp5bsZ78ExGMMaataSA2IIA== | 2026-02-13 07:08 | Development | D365 - Makina | Jana Sweid | Kurban Group | Support | Active | Pending Customer | 2026-01-08 16:36 | 4 | No | 36 | Normal | 2026-01-24 16:36 | 8 | 1
810cc226-beec-f011-8543-002248a2bddb | 1Z1mwjvu79d8at5Pvc+dX9OEoqg2B2YVw7ej+xJrJHjf1Zv6o8oIMaIW5SzKa6jJxw+faecf1o9NFDQDUCZd7A== | 2026-01-26 10:58 | Migration | Toters :: Relealized/ Unrealized gain loss | Abdo Khoury | Toters | Support | Active | Pending Customer | 2026-01-08 20:17 | 1 | No | 36 | Normal | 2026-01-31 | 0 | 0
b2853d1e-ccf0-44eb-982c-f67dd90a99ba | 9jVuP9X+jZ63P3S9t4JagqECP4f21VOJiidjcau6umFJIrKy3eHSXwtEJxI/5DNr8GhqSvUQzni+h/xsYrqeLw== | 2026-01-08 18:47 | R&D | Modoniq.com Scoping Session | Abdo Khoury | Info-sys | Support | Active | Not Started | 2026-01-08 20:47 | 6 | No | 36 | Normal | 2026-01-14 | 0 | 0
ab7fc81d-48ed-f011-8544-002248a2b3c0 | 2Y6ZwLRtsUDfCcsKBNWRK7/B1NllR7EDs8mz/1INywHBNKEFrz6FjJyh4TBMzwqoXOi++2aH0PbMdAsF+Af+vg== | 2026-01-19 11:02 | Development | muni - currency code must be specified | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2026-01-09 12:44 | 4 | No | 35 | Normal | 2026-01-16 | 9 | 1.13
14c6cf24-6fed-f011-8543-002248a2bddb | iE0DVfORRIBuXDw2/QC4Qq4I0zq2AE9q3ai3vrxbZaNzkrudRhvbT87eqfA7NZvaOXGhvIVVpZiysY7ZW/ijvw== | 2026-02-12 06:57 | New Request | Avis :: Vendor Automated SOA email | Fadi Hanna | Allo Transport | Pre-Sales | Active | Pending CR | 2026-01-09 17:23 | 8 | No | 35 | Normal | 2026-01-25 17:23 | 2 | 0.25
2b3346d6-77ed-f011-8544-7ced8d71b5a4 | 1D0uxWXd5I7kfI5A3OPuFVx0uP/7oX+MEqMuspDa39MkG0WYnej9cYYOE9miiIM2XcmCz1zbZDthhY65cGL2VA== | 2026-02-11 15:41 | Development | CR 0123CRJC3052025 | Rebecca Estephan | Hugo Boss | Change Request | Active | Pending Customer | 2026-01-09 18:26 | 24 | No | 35 | Normal | 2026-01-25 18:26 | 2 | 0.25 | 0123CRJC3052025
0cda24e4-92ef-f011-8406-000d3a666f28 | lfDbIjva2pZnzZwXPyVYJuIKV/pPk24TmJbnrrNNjH8YhVG0zjh6OFTiFXWn4oqGAgTJ3zyoFLidfWr6O+gSQQ== | 2026-02-11 15:41 | Workflow | Invoice Journal assigned to me | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2026-01-12 10:45 | 2 | No | 32 | Normal | 2026-01-28 10:45 | 1 | 0.13
b4abf004-99ef-f011-8406-000d3a6660b9 | rHe365mxH5MouWggou6tffnnbHTeRNyQbQQz+NDsxd/1QPNf6WorFjJXNeBWW1g2up6ivfz0JsiJOgQ6t2w4zQ== | 2026-02-11 15:41 | Development | FAR Template | Georges Mouaikel | Alfa | Support | Active | Pending Dev | 2026-01-12 11:28 | 4 | No | 32 | Normal | 2026-01-28 11:28 | 1 | 0.13
024addce-bbef-f011-8406-000d3a666f8e | gYgC4pVHZTlf9wpjyTeCB4/EYPPtMtNDGstkVQtL6jHkb7l0U1Tze2qAdzxSK/F5sScmUT8rFI4dLW10EaUpDw== | 2026-02-11 15:41 | Development | Issue on sum picking list | Jana Sweid | Second House | Support | Active | Pending Dev | 2026-01-12 15:37 | 4 | No | 32 | Normal | 2026-01-28 15:37 | 10.5 | 1.31
66bcab00-0bf2-f011-8406-000d3a666f28 | +bzqoowGnauqwIDt8P2XkLkCW9iIfQpB8lSM4m2Kw96J8Q1rWSuxXAQ8JSAXeZvclrDycHmLt0FqSpQHW6RKcg== | 2026-02-11 15:41 | Development | Municipality Accruals Cancellation Journals | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2026-01-15 14:09 | 4 | No | 29 | Normal | 2026-01-31 14:09 | 7.25 | 0.91
49aff71a-67f6-4659-b901-6ded06679c27 | wq05XiDsLgH3C8JOv4pitBgXr5MgOe2R3Ga1w44ypod1Wtaws4tIaxK4WMJaJe5DtRkTJHEQ9rQpn0ISia7itA== | 2026-02-11 15:41 | Development | FW: Adjustment GL journal Description - GE cancellation | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2026-01-15 14:30 | 4 | No | 29 | Normal | 2026-01-31 14:30 | 8.5 | 1.06
b6e66a28-15f2-f011-8406-000d3a666b50 | Zs6SRIWfQ528nLgvo/DpnTmEakMCD5bX/reYh7J/2INEXIemOYJSTufyeLZrvRQsX5OPun4/EUG0r2DzcOZ35g== | 2026-02-11 15:41 | Development | Update on SFA order chekout delivery date | Jana Sweid | Holdal | Change Request | Active | Requirement Gathering | 2026-01-15 15:22 | 24 | No | 29 | Normal | 2026-01-31 15:22 | 2.5 | 0.31
6de86bc9-41f2-f011-8406-000d3a666b50 | zR0S0UK1Y1tk35gH8T8/fakJ9gduJd+FMwXtpLo1LFhyRpsdd9Dl1zPrr+cPSogfyziArkRaIxGcKg5uYUC22g== | 2026-02-12 06:57 | Technical Issue | Fw: missing timesheet | Fadi Hanna | Acuative | Support | Active | In Progress | 2026-01-15 20:41 | 6 | No | 29 | Normal | 2026-02-21 13:28 | 1 | 0.13
93b98a28-b961-4908-9b46-ba8d9f619823 | htHgwcQKWQaIsRhQem3ffDvpe8tjv9fcg7GrehEV+WXwUW/pPkz/AWn8B5hfdij7k08JgdU17VIklwf8kTtlOQ== | 2026-02-12 06:57 | Functional Issue | Configuration of Financial Statements in D365 | Fadi Hanna | Etisalat | Support | Active | In Progress | 2026-01-16 10:07 | 15 | No | 28 | Normal | 2026-02-20 02:00 | 6 | 0.75
a8ebf8b5-c0f2-f011-8406-000d3a666f28 | KxgFwWnMzRkFLcmOadD7Ed0+cjjT3v8MCde7JRMDVnUqVQ8KCDXj1dOoJhkstMwY+roZbmEbVxtBjl/U8Tl3dA== | 2026-02-11 15:41 | Development | FW: FMC -MECAR aging rpeort | Jana Sweid | Kurban Group | Support | Active | Pending Client Confirmation | 2026-01-16 11:50 | 4 | No | 28 | Normal | 2026-02-01 11:50 | 4.5 | 0.56
b9b848c4-f4f4-f011-8406-000d3a666462 | +jxaFJq+jpO+qrmSioCCeqb3/PNw0STuQ1NY1MsV+QbGLWhC1ItVT5B9hzy257G84e/An9Ly2EpwElLSqUxYqw== | 2026-01-19 07:54 | New Request | Falco :: Support Briefing | Abdo Khoury | Falco | Support | Active | Not Started | 2026-01-19 07:08 | 1 | No | 25 | Normal | 2026-01-19 | 0 | 0
24e40739-fcf4-f011-8406-000d3a666ee6 | 6Ms1vksr8egPKBphJIcSgRexfIgpAPq1P83HVORivNTbBy9/0Bngi/FRSejbBSUC+tt0PYvUffsTfYHRg0JVDA== | 2026-02-05 11:03 | System Administration | Engicon :: Remove Admin Security Roles | Mennatullah El Bahr | Engicon | Support | Active | Pending Customer | 2026-01-19 08:01 | 1 | No | 25 | Normal | 2026-02-02 02:00 | 0 | 0
c4be538d-26f5-f011-8406-000d3a666d3c | oOw6Buro/z69aaGD4UpuHEY4x2rUsxhPGX4vnp6Gw6j0nuZ+tSwX7UniST+KlqXnbV9gN/g2JLZpU7Wwh4/Vcw== | 2026-02-11 15:41 | Development | Run Prepayment | Georges Mouaikel | Alfa | Support | Active | Pending Dev | 2026-01-19 13:04 | 4 | No | 25 | Normal | 2026-02-04 13:04 | 15.5 | 1.94
c66d9e2c-2df5-f011-8406-000d3a666ee6 | FSLPXH48HOr+szFcjIoJUlsVrMqNIE5sJNJTN27j3oF04ldVPZ/+WkU/mGLpxXqieo1ec0CglWTj0Zw/biBAwQ== | 2026-02-11 15:41 | Functional Issue | Financial Dimensions E.Site | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-01-19 13:51 | 2 | No | 25 | Normal | 2026-02-04 13:51 | 0 | 0
ad0d57bc-36f5-f011-8406-000d3a666f8e | pA/iMYrMp8I0ylFlYPdHslXZSTY7FwXVhZXrWNnt7UHNxfdu5AwMp50vqXFBOA5UeWOiK2BylzDU9pGET4oClg== | 2026-02-11 15:41 | Functional Issue | Accrual run date | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-01-19 15:00 | 2 | No | 25 | Normal | 2026-02-04 15:00 | 2 | 0.25
276d6106-3ef5-f011-8406-000d3a666462 | 2/fV3+Mll8y46TSdkCMYqpUPbBeKuhbsbPqDyln4gKd6901yNWKLEpkpNTTyyBEwFLcvJ+aRNYfNebhYsTpC6A== | 2026-02-11 15:42 | Functional Issue | Items from Giesecke supplier are exempt from Tax | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-01-19 15:52 | 4 | No | 25 | Normal | 2026-02-04 15:52 | 0.5 | 0.06
e0488e7b-98dc-45c7-9fba-6b06337ccef1 | JdRB78aV96fkbYXTMtgtQzL3GAj7Dsd0CQONoTsdljzmE6vsXuRTS+9rNmCeV/g7YvzJPX0iVHztD/AuAH8F7g== | 2026-02-10 07:07 | Technical Issue | Material Adjustment Note | Fadi Hanna | Etisalat | Support | Active | In Progress | 2026-01-19 21:37 | 4 | No | 25 | Normal | 2026-02-15 02:00 | 2.5 | 0.31
9b0915a0-cff5-f011-8406-000d3a666f28 | 9Au/jg1X+s3p256Fk3UwXJPLzenWym9VS3d2MSjxg7s6K62JHs/SToOn2Alr4/Q7qL/WW7HrHKW2NAoV+i81RA== | 2026-02-11 15:42 | Development | FW: Allocation voucher | Jana Sweid | Bromine | Change Request | Active | Estimation | 2026-01-20 09:14 | 24 | No | 24 | Normal | 2026-02-05 09:14 | 4 | 0.5
2ab5df3b-d0f5-f011-8406-000d3a666d3c | YYdiHRNYcgwkBiAt/AI1BTSUP0V9dWlonFo4RtCM7OnkrwtcJi6+gZs5Nk+oViPBFnZAMxt/VHboqDB46n/bfA== | 2026-01-30 13:16 | Development | Carry forward process inquiry | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2026-01-20 09:19 | 15 | No | 24 | Normal | 2026-01-23 | 13 | 1.63
95477350-e0f5-f011-8406-000d3a666ee6 | 27YmN2DUQmDnoZKQlnK6JvjqgMs2IE5DIzhKJn4na0/QR4zMz8VAAJy0frfDkKveoigRpO37AxOgCWTAvqazjw== | 2026-02-13 14:43 | Development | Budgeting control warning Notification | Fadi Hanna | Bromine | Support | Active | Pending CR | 2026-01-20 11:14 | 8 | No | 24 | Normal | 2026-02-05 11:14 | 8.5 | 1.06
8e202cd2-e0f5-f011-8406-000d3a666b50 | RMOghRfB8+UnTrarMK/ZC9d2tFuOG7sPWUxd6WTmkr5tHoT2QQfrHWSqT7cqGiDSO9OGys16EKuM8Rnjse5I/A== | 2026-02-11 13:53 | Development | Automating the extraction and generation of the Related Parties(customer invoice details) report to ensure accuracy, completeness, and timely availability | Rebecca Estephan | Bromine | Change Request | Active | Estimation | 2026-01-20 11:17 | 24 | No | 24 | Normal | 2026-02-05 11:17 | 9.5 | 1.19
91202cd2-e0f5-f011-8406-000d3a666b50 | cF46qsz6fErIfwQ6737QUUtpnZxJ/UDw7qvNGcUZ72wsvCbNbVgG1wmYLH+txFn0WXqUvP6xAOdcx/ZfsDaCig== | 2026-02-11 15:42 | Development | Automatically generate AR invoice with attachments through D365 | Jana Sweid | Bromine | Change Request | Active | Estimation | 2026-01-20 11:17 | 24 | No | 24 | Normal | 2026-02-05 11:17 | 3.5 | 0.44
74b1c94e-bff6-f011-8406-000d3a666f8e | hUQVCOwGvnG5YzoqRMNJmYNmnMlDT3VZjuVc7uX5C+F2Dea8KuhpwDS67dtqRQWZWNYqB205Yl4zFboCA6OSnA== | 2026-02-10 07:01 | System Administration | D365 DB Capacity | Fadi Hanna | Acuative | Support | Active | Pending Client Confirmation | 2026-01-21 13:50 | 5 | No | 23 | Normal | 2026-02-13 02:00 | 10.5 | 1.31
32325f4b-d5f6-f011-8406-000d3a666ee6 | z7STOljhHdBnt5y9ipyW534ZsdTu252g+tr+l9wQFn7LcAwtJFCflAeyVUS3rt7OdbANd6lbFl3qd1woY34OfQ== | 2026-02-11 13:57 | Development | Holdal :: Qualifying Points Process | Rebecca Estephan | Holdal | Change Request | Active | Estimation | 2026-01-21 16:27 | 24 | No | 23 | Normal | 2026-02-06 16:27 | 9 | 1.13
6d16275e-74f7-f011-8406-000d3a666d3c | CrWhEY2umjYadoTsngplq8+GU3Sd8bNbpYeGGgl1gPvbJ+3tJceeY5xLXbcETGitecl4j4S4AVUhIGWZlvV9aA== | 2026-01-26 10:42 | Development | Toters :: P&L and Balance Sheet | Fadi Hanna | Toters | Support | Active | Requirement Gathering | 2026-01-22 11:26 | 5 | No | 22 | Normal | 2026-03-31 | 0 | 0
16e28bb8-32f8-f011-8406-000d3a666f28 | dzBWH+O8aiKW0NwGbQZtQ5obSoQ3kLYDH5eepJ13elL1kab86ATDWh646Vl4qfpX7TguEpmwzHjSjLnNoTI1xw== | 2026-02-11 15:42 | Retail & POS | FW: Swap Pos system (a.moratto with ABC Dbayeh) | Rebecca Estephan | Hugo Boss | Support | Active | Pending Client Confirmation | 2026-01-23 10:09 | 2 | No | 21 | Normal | 2026-02-08 10:09 | 1 | 0.13
311d3f8b-50f8-f011-8406-000d3a666f8e | Fm5E8fG52aeOVgAETRGbno56OYymLonc6r2aWoT83UmsY4r4hDiYC+UH+tiG+Wn8V8JINve4g7LyMYZaHQG+fA== | 2026-02-12 17:22 | Budget | FW: D365 | Georges Mouaikel | Alfa | Support | Active | Pending Client Confirmation | 2026-01-23 13:42 | 3 | No | 21 | Normal | 2026-02-08 13:42 | 4.5 | 0.56
81cc9157-5bf8-f011-8406-000d3a666462 | qMgAj82uC5woNszfJDrpTpK1JGuoVBa1y9EktJUC+1Q1Jsea4bKk2Q/+5j6vyMfKSAfBFjuQlxxCVYWAT0TIfA== | 2026-02-11 15:42 | Budget | Same issue / several line items | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-01-23 15:00 | 3 | No | 21 | Normal | 2026-02-08 15:00 | 3 | 0.38
855d55ee-58fc-f011-8406-000d3a666f8e | q6KDwCt3EsqK7RGy6TWSidpj94MxCrzK5jVZZosaQDDOuco9DQSA7EF6ptn93pKgrdpNqW1GGV8jmobK+vPpfg== | 2026-02-11 15:42 | Development | Loading Report - Additional Columns Request | Fadi Hanna | Holdal | Change Request | Active | Pending CR | 2026-01-28 16:52 | 24 | No | 16 | Normal | 2026-02-13 16:52 | 2.5 | 0.31
929a29a5-f9fc-f011-8407-000d3a666ee6 | Z/8D21wBixD+b4R61FHhTgn/Jm7jqGIF38ut3uJapZLFYw+TR3Y49TknlMkqmS+QVLiTGecIW+kT6Xn5WftjzA== | 2026-02-11 15:42 | Development | Expired contracts | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-01-29 12:03 | 6 | No | 15 | Normal | 2026-02-14 12:03 | 0.5 | 0.06
b37b0750-07fd-f011-8407-000d3a666f28 | ds/xytlmW4M32I859n1q4tqRJxSAdmVXzTSbkFImte3mE0qNXhJhp+j6Xm/PZ2UJ2Kg6xyjgvhgsWQGHUUP1fA== | 2026-02-12 08:40 | Development | On hand list | Jana Sweid | Joudi International FZE | Support | Active | Pending Dev | 2026-01-29 13:41 | 4 | No | 15 | Normal | 2026-02-14 13:41 | 17 | 2.13
e2742d95-17fd-f011-8406-000d3a666f8e | MyJ2L9roSyqLgqi3UVmerG1X37bBa99LIJ21Q/FJLUWtVNMcEacSczVAb7u18G+/gxayhWfq/Zm7cUrUIqCrOg== | 2026-02-11 15:42 | Development | FW: Contract management /Power modules invoicing 2026 | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-01-29 15:37 | 6 | No | 15 | Normal | 2026-02-14 15:37 | 0 | 0
9831c2cf-bafd-f011-8407-000d3a666462 | DgaqHwkfjBWPBgNBknHBaCkzj+cdUo91HHvUqSGZKnlDU0CIlYz8qbAeACu1XkK776nP5EEPL1PccWO1zxoekg== | 2026-02-11 15:42 | Development | Serial Number Incorrect Invoice printout dispaly | Rebecca Estephan | Holdal | Support | Active | Pending Dev | 2026-01-30 11:06 | 4 | No | 14 | Normal | 2026-02-15 11:06 | 0 | 0
2a8e3df8-effd-f011-8407-000d3a666f28 | a8ebgCgik9PLp7H82KGbVRyCeoY3yA6CckSUpAdu5Z0Moe2NDYC3BMdczEv6YZ1SOIObpTBXBFnv2A6XwfywIg== | 2026-02-11 13:57 | Development | Holdal Wallet Process | Rebecca Estephan | Holdal | Change Request | Active | Estimation | 2026-01-30 17:26 | 40 | No | 14 | Normal | 2026-02-15 17:26 | 5.5 | 0.69
ad5a8a9d-fdfd-f011-8406-000d3a666f8e | dJvQU8dq3krrP4OHedkC3CKaCSTOhq6tFcZZg2lMUfjR6IujEap68C1VYTKIyL1zTHCmkRkLJU1kPzZDjUv66g== | 2026-02-11 15:42 | Development | Fw: Transfer order report issue | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-01-30 19:04 | 5 | No | 14 | Normal | 2026-02-15 19:04 | 0 | 0
dcbc23b1-fffd-f011-8407-000d3a666ee6 | lnBn1SMccj1i1elC9C4YDq8VQTyQt8tjNX3bmNfC4M/kErPq3JRxwXkihAY+iRLcw1IJHMXPHOjlFAbYPMWglw== | 2026-02-13 14:35 | Development | Toters :: Manual Vendor Creation Number Sequence | Fadi Hanna | Toters | Change Request | Active | In Progress | 2026-01-30 19:19 | 24 | No | 14 | Normal | 2026-02-18 02:00 | 0 | 0
d0a0926e-7efe-f011-8407-000d3a666f28 | UxHSAJMkUMh9D7vN8E45qL4SWf15gP0niZvi3aZLs74eysG/6LaLRNr5T6haXCQcCLU70cWEngvHk2+AbrNrJw== | 2026-02-12 08:39 | Development | Issue with Product Name in Released Product V2 | Jana Sweid | Second House | Support | Active | Pending Dev | 2026-01-31 10:26 | 4 | No | 13 | Normal | 2026-02-16 10:26 | 6.5 | 0.81
ebb6a10c-0000-f111-8407-000d3a666f8e | UebkVzqtlETIsMupKuEDJYYr52xxh1zwMw6lJxVlTsM8DB1VOk7K4avUo79X6i3X4MkWVE0P6URzcQtQ93ZXMw== | 2026-02-13 14:43 | Development | aging table format | Fadi Hanna | Kurban Group | Support | Active | Pending CR | 2026-02-02 08:26 | 4 | No | 11 | Normal | 2026-02-18 08:26 | 2.5 | 0.31
c34c1ef0-0200-f111-8407-000d3a66611a | S82/dQGzT200u0ZwPW0S8HgVchcLOaZtB2fF4t2RlePD0QTQ7QhSmkWfdTp/uHhEeqT/BUJDkcxmzSz3LO91jw== | 2026-02-11 15:42 | Development | Updates to be done in the Expense by Type Report | Fadi Hanna | Holdal | Support | Active | Pending Client Confirmation | 2026-02-02 08:47 | 5 | No | 11 | Normal | 2026-02-18 08:47 | 3 | 0.38
7e44a43b-2500-f111-8407-000d3a666f8e | JmY7/Uzonb0pFREij/mPm6M6ExakZTTfnwgytH4sEJKPDpPji/HJW/NDb7ASnpnWVUL3lnVwKl8ECv/f/ZCTqw== | 2026-02-12 12:43 | Workflow | Alfa Workflow/email notifications | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-02-02 12:52 | 10 | No | 11 | Normal | 2026-02-18 12:52 | 0 | 0
2c7d4fef-4100-f111-8407-000d3a666f8e | PcQpe2DcuTiR2GgvjToBYyz5fXGXudKHSNyeWWb97Z6eLiQK/dGrfkRH+OMQ2GUfVnNpK+3h6Hg/wrO3DhH2Eg== | 2026-02-12 08:11 | Development | FW: F&O x Shopify - Stock Update | Jana Sweid | Holdal | Support | Active | Pending Dev | 2026-02-02 16:18 | 4 | No | 11 | Normal | 2026-02-18 16:18 | 3.5 | 0.44
33f72991-88ad-4031-aa12-c74e097fd308 | D6DgyS7E8WsqB/jwRcscim9E7bvHlvuDjxWAI7xcN4EqOHtPXKva1VYKo9817h7GCK+LsdkGyD8cqztMNqGgvA== | 2026-02-10 10:40 | Training | Retail Features | Fadi Hanna | Info-sys | Internal Support | Active | In Progress | 2026-02-02 17:10 | 16 | No | 11 | Low | 2026-02-06 02:00 | 7 | 0.88
787eea1a-618c-4b36-8c2c-cd8489c36a62 | VFqPQEgrqsnUpb0yr5QVhvHqxx2NMbjqB8UdNfJYti0rw0JJ4mpILY13g8SmDSfjt3jlnKM9f8bQ1xRu4t5OYQ== | 2026-02-12 12:42 | Budget | Meeting Carry Forward and Actual Expenditures | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-02-02 21:44 | 50 | No | 11 | Normal | 2026-02-18 21:44 | 52 | 6.5
3be51f03-d600-f111-8407-000d3a666f8e | pzlbUVq7Z5As5JBM7LEjw2zpIr3CyPF7fY2e/sUb2tgKpn0eKCVqiZ7AXb3rsvAiNaIcPEi7ne8joGfpuFuNoQ== | 2026-02-11 13:52 | Development | FW: Daily production reports | Rebecca Estephan | Bromine | Change Request | Active | Pending Client Confirmation | 2026-02-03 09:58 | 24 | No | 10 | Normal | 2026-02-19 09:58 | 3.5 | 0.44
6474866d-dc00-f111-8407-000d3a666ee6 | TYkKA+Pha3YRNlpvXmkRZ4isrWygpAC8BSdMoQNbcuZ5Sc6450sHCfsMW/3cr6teFymX9q/Yvyx283DgGRAjlg== | 2026-02-11 15:42 | New Request | Portfolio Alignment with New Charging System | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-02-03 10:44 | 10 | No | 10 | Normal | 2026-02-19 10:44 | 0.5 | 0.06
59940e94-de00-f111-8407-000d3a666462 | ma1GNwSXxJAcTlHlMvQ+A2hLVgLmzuYXnr4JV65bma5uKEhJ3eWj6oRvXcjblOnx/k+8GnqSGnDsM3xr38LG7g== | 2026-02-12 14:40 | Functional Issue | FW: SR # 409172 | Rebecca Estephan | Bromine | Support | Active | Pending Client Confirmation | 2026-02-03 10:59 | 6 | No | 10 | Normal | 2026-02-19 10:59 | 2.5 | 0.31
0430577f-c9de-4b04-a605-097cce0a0439 | FRIYLt/FtfJsgZabgkVGjI1YLxPYGLJBhd5iw5ubvTIBANnuOJDqFWE2chKaciKYE63vqt55ZCOtikpZDfNB/g== | 2026-02-11 15:42 | Development | Request to Adjust Internal Transfer Import | Rebecca Estephan | Holdal | Change Request | Active | Pending Customer | 2026-02-03 11:50 | 24 | No | 10 | Normal | 2026-02-19 11:50 | 0 | 0
83dbd4cc-e600-f111-8407-000d3a666f28 | XvQi4fLR/yg+66bZ2G4zcFfwQjldQA8EwgisYKRI05IX2nn6Ff76x/4dcT/G4f+RZIsoWEhN6afDkEpjUeINGQ== | 2026-02-11 15:42 | System Administration | ERP Production DB locks | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-02-03 11:58 | 6 | No | 10 | Normal | 2026-02-19 11:58 | 0 | 0
b7cbca91-f000-f111-8407-000d3a666f8e | oQR01dDAf5REO6wtnZNmMFjrIY2OHHdI+fWKNAKizdsTAB7jXUc+qpZbQI8wGbECbPdFtICR9ycELsv5Gz3iJw== | 2026-02-13 06:57 | Development | FW: Time Attendance Report | Fadi Hanna | Holdal | Support | Active | Pending Client Confirmation | 2026-02-03 13:08 | 6 | No | 10 | Normal | 2026-02-19 13:08 | 5.5 | 0.69
4a9318c3-ce01-f111-8407-000d3a666462 | +9Vz2KKio9MIJeTeYE98pA+A5TgaRT6NeLlvdVjGguzsq9nLpVZM1ZZlLf5nE8RYhha1FeqOfwNvz0DvZzAPYQ== | 2026-02-11 15:42 | Development | Holdal Welcome Bonus | Rebecca Estephan | Holdal | Support | Active | In Progress | 2026-02-04 15:38 | 24 | No | 9 | Normal | 2026-02-20 15:38 | 6 | 0.75
29e669cf-6c02-f111-8407-000d3a666ee6 | PlxR5Ig49f+1fxw56pCKxdyl+JqMvWuYm1zjTQjAJxq9kexerBVo7f4Q4xh+gG4MrVbsLoLBFtyEUHHIoaiitQ== | 2026-02-12 17:05 | Development | Historical - PRs and PRs lines | Georges Mouaikel | Alfa | Support | Active | Pending Dev | 2026-02-05 10:30 | 4 | No | 8 | Normal | 2026-02-21 10:30 | 0 | 0
79ba20f3-7b02-f111-8407-000d3a666ee6 | oXoK7NEdNl2QBaYMlBoUq1kVCBFudfbv5B0JB46p8+KWts6ZxPIZmQxoMtUGcVXgceCeTmrXFmktCcTHWAfxyw== | 2026-02-13 13:00 | Development | FW: Tag SFA promo lines | Rebecca Estephan | Holdal | Change Request | Active | Pending Dev | 2026-02-05 12:18 | 4 | No | 8 | Normal | 2026-02-21 12:18 | 1.5 | 0.19
d41f8ac5-8502-f111-8407-000d3a666462 | LJ8Nqi/sm7LHBAo4OWaWJHWJDi7oHTKVNFzlrdPTqDrBeaskzTMnZEYnlZnrNNM8sYs4QKm0nhlnkKWnY6jmgw== | 2026-02-13 14:37 | Functional Issue | FW: Deletion of approved and processed Transfer Orders | Fadi Hanna | Etisalat | Support | Active | Pending Internal Approval | 2026-02-05 13:28 | 6 | No | 8 | Normal | 2026-02-21 13:28 | 2.5 | 0.31
143a51e4-d8ae-4b31-9440-b982a6849fd2 | mmQQ4vAGygGxO2X92YjYJTReEf9oxLMewV8g/NPk4nzVNB80OoMOBW7S7v6qDswre6v7PSLV/h4UpaFVNrudIg== | 2026-02-12 08:43 | Migration | Toters :: Sales Tax Groups | Jana Sweid | Toters | Project | Active | Not Started | 2026-02-05 13:48 | 2 | No | 8 | Normal | 2026-02-10 | 1 | 0.13
20b41b73-9a02-f111-8407-000d3a666ee6 | ztGq/3YIwLIRSrR+DTYjVMR9lSJ424RT08YQJqmLd0qQxcxzN9LBqx5h8qcsl9xiXAffOXIHOZM65VgOljyHxw== | 2026-02-11 15:42 | Development | Holdal :: Gift With Purchase | Rebecca Estephan | Holdal | Support | Active | Pending Client Confirmation | 2026-02-05 15:56 | 5 | No | 8 | Normal | 2026-02-21 15:56 | 2 | 0.25
8c24fa8a-aa02-f111-8407-000d3a666f28 | VJ0xtRD5Q1wFqslULnJAJ2tUiu4HCVmc82FZbEjKiPckPRG5Kvr0jIkrQlIaGJo6BQwRycqyOYTXYbKbS/uWOQ== | 2026-02-13 14:32 | Development | Hugo Boss :: Minor Enhancements | Fadi Hanna | Hugo Boss | Support | Active | Pending Dev | 2026-02-05 17:52 | 4 | No | 8 | Normal | 2026-02-21 17:52 | 1.5 | 0.19
7c86413d-c804-f111-8407-000d3a666462 | MUpJVnxUZv2frXddAYsUFqx4R08aP63pE1hNV/odmclRBp3VXVE9jURLmj4f5f2+MIq9Y9S8kmoRUlUmjgtz+Q== | 2026-02-11 15:42 | System Administration | Power BI user | Fadi Hanna | Joudi International FZE | Support | Active | In Progress | 2026-02-08 10:29 | 2 | No | 5 | Normal | 2026-02-24 10:29 | 0.5 | 0.06
adc5a1a7-d004-f111-8407-000d3a666f28 | AuMXxGRTeM8rWNcvkhOYbULl1JfGger2DTLOWVvUje1TEG2VSFbT7zuECZmVABguRm1Cryhk+TMHwbspt3DRng== | 2026-02-13 07:07 | Development | Automatically sending pre-gate . | Jana Sweid | Bromine | Support | Active | Estimation | 2026-02-08 11:29 | 5 | No | 5 | Normal | 2026-02-24 11:29 | 2 | 0.25
ee1e203e-ab05-f111-8407-000d3a666f8e | hKZIU6hTMWmtOKY8dziCfFqrY+DWeNH5CFTzvAluzDeIjwM6C+C/rTrsxYI/HinCTi18/W+OlH3yBKqVaciGCQ== | 2026-02-11 15:42 | Development | Addin Batch and Expiry date on PO lines | Fadi Hanna | Holdal | Change Request | Active | In Progress | 2026-02-09 13:34 | 24 | No | 4 | Normal | 2026-02-25 13:34 | 1.5 | 0.19
37bc49c9-5806-f111-8406-000d3a666d3c | F6E8ndBm7cN62GEC1i7P9LNCFuinaL3sNUxyenLv6/3+ioEvyQlwTNjfffR2tazR2sc+GnSSgPgudv18++bRcQ== | 2026-02-13 14:25 | Development | New Entity Dynamics365 | Mennatullah El Bahr | Engicon | Change Request | Active | Pending CR | 2026-02-10 10:16 | 24 | No | 3 | Normal | 2026-02-26 10:16 | 3 | 0.38
a7158634-5a06-f111-8406-000d3a666d3c | KU+9K8ShuCTPVbMn7fEIACvH8qvgIn+GrVE7Xdfd5H255XD6JnfLrXzbYx/fQ/RvAFW8R+VlpOk7Qi5Wqh8zfw== | 2026-02-12 08:13 | Development | FW: Pre-gate activation issue | Jana Sweid | Bromine | Support | Active | Pending Client Confirmation | 2026-02-10 10:27 | 3 | No | 3 | Normal | 2026-02-26 10:27 | 3 | 0.38
e38f6eee-5d06-f111-8407-000d3a666ee6 | 2L+b1NYcmb9Psw9Bld5njNse62uK5TNTz+e070/1Kat5vxuzcz3eNxnnIsCnSHX07ZD8bJlxBpi37vYbqgRxaw== | 2026-02-12 13:17 | Functional Issue | Transfer Creation | Fadi Hanna | Hugo Boss | Support | Active | In Progress | 2026-02-10 10:53 | 4 | No | 3 | Normal | 2026-02-26 10:53 | 4.5 | 0.56
2620bd74-6006-f111-8407-000d3a666f8e | VCkleHDnhZcuicyXIsE5MlCzZvS+Jo8FfJaxXd0vqaBkTSvpoCym/pMFMF5ksNlnSxyOkWLoNMcdxczhRwZmfQ== | 2026-02-12 14:39 | Development | MFG date not provided starting 14/1/2026 for the item 2037_ISO23 and 2037_ISO175 | Rebecca Estephan | Bromine | Support | Active | Pending Client Confirmation | 2026-02-10 11:11 | 4 | No | 3 | Normal | 2026-02-26 11:11 | 4 | 0.5
7a63369d-6406-f111-8407-000d3a666462 | EAA4RwVk2IEvH86eLiz2ddippVI8AWbFMUGv6zs0LBWaBrSwa7aJ6CTm/spJuk7jopLKY3Lj431yjKDaf1xlFA== | 2026-02-11 16:09 | Development | Packed Tags Received State | Rebecca Estephan | Bromine | Support | Active | Pending Client Confirmation | 2026-02-10 11:41 | 4 | No | 3 | Normal | 2026-02-26 11:41 | 1 | 0.13
4329dc51-6c06-f111-8407-000d3a666462 | RBzjjDWCEoGEAZKvqAPXV3Y8KOARtmiY/E+BACCXFfamaZ50jpt/8GSFeVPGAaS7BqCCtr1fDnmV3G6vT4ZD/A== | 2026-02-11 16:14 | Development | FW: NaBr calculation | Jana Sweid | Bromine | Support | Active | Requirement Gathering | 2026-02-10 12:36 | 10 | No | 3 | Normal | 2026-02-26 12:36 | 0 | 0
d8176181-7706-f111-8407-000d3a666f28 | lME5k359eo7Gm4QxEVj69dvWawC4YNwRzjVWvQETxkCw6gWiGlk4hHOUVox4Pgl8moRgk64pRPPdcl0qowB/zw== | 2026-02-13 14:25 | Development | Engicon :: Payroll Integration Server Link : Prod Env. | Mennatullah El Bahr | Anas Jaafreh | Support | Active | Pending Client Confirmation | 2026-02-10 13:56 | 4 | No | 3 | Normal | 2026-02-26 13:56 | 2 | 0.25
add49702-8406-f111-8407-000d3a666f28 | xH/IKYUdLB1GfWbhrvt+DZ/HUajgqgnPXD9/se/CJzpMNUwKFJE2m32gLdQjjuwzDYt/gn+yE/vOQJvx4nfl3w== | 2026-02-11 16:14 | Development | MAARAB- As built. | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-02-10 15:26 | 5 | No | 3 | Normal | 2026-02-26 15:26 | 0 | 0
87bfa000-8d06-f111-8407-000d3a666b50 | hyOqSUW/oD5yRsfH7XlDTKsdUsdSbiKd5RprDvFpj7ygVq1cXn2Rj92R+mu7zkXfCBLjRRMvTEOfSWSe2sISXw== | 2026-02-11 15:42 | Reconciliation | Wrong Account of DOE | Raji Aoun | Hugo Boss | Support | Active | Not Started | 2026-02-10 16:30 | 8 | No | 3 | Normal | 2026-02-26 16:30 | 0 | 0
65c1ed1b-8d06-f111-8407-000d3a666462 | CXDI2Gf5X36FUiK4r56UZa+mTbELMi1UqAnbswbThTp5Bj72O0yBTYwoptIcYkAyJKeKTVm4Pcsy06Job5C64Q== | 2026-02-13 14:43 | Functional Issue | Incorrect Inventory Transaction for PO | Fadi Hanna | Holdal | Support | Active | Pending Client Confirmation | 2026-02-10 16:31 | 8 | No | 3 | Normal | 2026-02-26 16:31 | 3 | 0.38
2c50aafe-9206-f111-8407-000d3a666462 | 4piNpFCaAXDbuO9LAbSg0Z1vrgZAb+/49HPtziDlce7wLeYEDRukFPiuOeqAIbMGNShQJy3u+7i5sBxUnSCJJA== | 2026-02-11 16:14 | Development | Request to Update Cheque Printing Layout – Urgent | Mennatullah El Bahr | Engicon | Support | Active | Pending Dev - Require Delivery Date | 2026-02-10 17:13 | 16 | No | 3 | Normal | 2026-02-26 17:13 | 2 | 0.25
9a4f00bd-3607-f111-8407-000d3a666f8e | nm6zcxvFAQ4kXSlTYNS/f94LsG68v4nGz2Sk2oKG5C/AIX3rMTyabYL+5ogeEjjLEbFDZ3FSHFW0gtc2K1pxYQ== | 2026-02-13 14:26 | Functional Issue | Entry ALLO-072020 | Rebecca Estephan | Allo Transport | Support | Active | In Progress | 2026-02-11 12:45 | 4 | No | 2 | Normal | 2026-02-27 12:45 | 1 | 0.13
060034d2-3707-f111-8407-000d3a666ee6 | Vxpem4HPLiLxo/O6XI1sAwWmA8MqoawoUxOTAcJFBfIm2QsWhuYuqEHrOK68u+Q++k90hCKMBN6VtXxNFpWcAg== | 2026-02-11 16:12 | HR & Payroll | FW: New Employees Setup Plans on Dynamics HR | Jana Sweid | Hugo Boss | Support | Active | Pending Client Confirmation | 2026-02-11 12:53 | 4 | No | 2 | Normal | 2026-02-27 12:53 | 2 | 0.25
8ced28b1-3907-f111-8406-000d3a666d3c | wuFulrLZqmRHIn0QZhRoEaBeoVmXjqebXhTFUfyVAeJUrNn4DwUAFa+bo0zUjhbnHowbse1TfQD4aeYNRpIgwg== | 2026-02-13 14:27 | Fixed Assets | Fixed assets register reevaluation 2025 | Jana Sweid | Allo Transport | Support | Active | Requirement Gathering | 2026-02-11 13:06 | 8 | No | 2 | Normal | 2026-02-27 13:06 | 1.5 | 0.19
bb6283d9-4e07-f111-8406-000d3a666d3c | BXRNsuacBiyPe9doY1ruoyumreRQx2lDP0Im73Q1THliFvTLTJJPOPtnWxeh5dLN3T60Bxw6/8aIRcCR4uEDhw== | 2026-02-13 13:00 | Development | FW: Holdal Double Birthday Points | Rebecca Estephan | Holdal | Change Request | Active | Pending Dev | 2026-02-11 15:38 | 4 | No | 2 | Normal | 2026-02-27 15:38 | 1 | 0.13
56a2e408-f207-f111-8407-000d3a666f8e | 7LxaSCA0o+Jh4DON2a3pbl1pkzdogMIWzWOs4UvAj+LRFx23YYSX76zxWvCtpZZSc0TuGJQeLQCiGDu1yWcakQ== | 2026-02-12 13:04 | Reconciliation | FW: Wrong average cost | Abdo Khoury | Abdo Khoury | Support | Active | Not Started | 2026-02-12 11:06 | 8 | No | 1 | Normal | 2026-02-28 11:06 | 0 | 0
b99f4af6-1208-f111-8406-000d3a666d3c | hv4GV467BKarNvOViq8W/VY7n+1ZSpyhTWBwAuOf6DNd0MrzOhEPgkUaOMRklsWJpIoNCV5XmYbjNp10a91e5Q== | 2026-02-12 13:10 | Development | FW: LMD orders tagging | Fadi Hanna | Holdal | Change Request | Active | Requirement Gathering | 2026-02-12 15:02 | 24 | No | 1 | Normal | 2026-02-28 15:02 | 1.5 | 0.19
78664126-1908-f111-8407-000d3a666f28 | zuI0HD2WO0AWFIzNCyuTmRTZKqHQoJSFXwlj01tB1yEKB3fzMhMeuq27dsZzn6VH2TxlLDzeMplATpoKhpuLRA== | 2026-02-13 17:51 | Functional Issue | URGENT: Tracking Dimension Group Update for Production Items | Rebecca Estephan | Holdal | Support | Active | Not Started | 2026-02-12 15:46 | 1 | No | 1 | Normal | 2026-02-28 15:46 | 0 | 0
f234056b-b208-f111-8407-000d3a666462 | OqSNJ+haLIdhKdNeDsULX7BMhQcdRduA99rYXZHF+uKFX2YaujCqOEZ9e3CwplA2a/Hbxb9GGtCbINx8/zOajg== | 2026-02-13 17:49 | Functional Issue | ISSUE ON MRP SALES PERIODIC | Jana Sweid | Second House | Support | Active | Not Started | 2026-02-13 10:03 | 16 | No | 0 | Normal | 2026-03-01 10:03 | 0 | 0
cd32569d-cc2e-4b6e-9979-9335f94105b3 | 4qtIMJp4IKT5I0AJT5fiFCc0WOUeOEid68fMDToaw5ohpreJuBZ+945QvB6qdc5GDKdtV3JeN1tzF8vIm7A9fQ== | 2026-02-13 17:51 | Development | Re: Automated batch job for data maintenance | Georges Mouaikel | Alfa | Support | Active | Not Started | 2026-02-13 12:00 | 8 | No | 0 | Normal | 2026-03-01 12:00 | 33 | 4.13
5af021e3-d008-f111-8407-000d3a666ee6 | Lsd2aOERhIcHONJDhq+lXsA9aBXSAs5k2Seqj3pDt0EqnryT3MX5+9prfjFVsD8l2twIklraJ9Ou/U9jwOeVCA== | 2026-02-13 15:04 | SFA | FW: SFA Truck Movement | Jana Sweid | Bechara Ayoub | Support | Active | Not Started | 2026-02-13 13:41 | 2 | No | 0 | Normal | 2026-03-01 13:41 | 0 | 0
a8fca62e-d208-f111-8407-000d3a666462 | tw2F9S80bEQPvTG4AUpcyMO11fBmeSEG3ihipHMsFwqq4wdBeFrPA/PEjSHwRQ64frC7Ya3WnUh7Hj2sKGrL8w== | 2026-02-13 17:52 | Development | Fw: New brand/warehouse | Fadi Hanna | Holdal | Support | Active | In Progress | 2026-02-13 13:51 | 4 | No | 0 | Normal | 2026-03-01 13:51 | 1 | 0.13
3e76c5c7-a927-48cf-b0ad-885ca61ee435 | w9P110D2Pn5A71yseNWcXN8oVLtoj7Mu+U/cRr7Q/eRQqj4jdcAgfBggehQo8YpqKjjN92GoatWm0ZaNYXoX/A== | 2026-02-13 17:08 | Development | Holdal :: WMS Flexible Scanning | Rebecca Estephan | Holdal | Change Request | Active | Not Started | 2026-02-13 19:06 | 6 | No | 0 | Normal | 2026-02-20 | 0 | 0

## hiddenSheet (hidden)
incident:L0SSXNCB60hwfI2lPE5K4wHKLFRDPlNMbee8Kz7lJWwNbIrAdvTFNXCjY2ntr/8Dqayayg9iyuOsOX4cliS+jg==:incidentid=%28Do%20Not%20Modify%29%20Case&checksumLogicalName=%28Do%20Not%20Modify%29%20Row%20Checksum&modifiedon=%28Do%20Not%20Modify%29%20Modified%20On&casetypecode=Case%20Type&title=Case%20Title&ownerid=Owner&customerid=Customer&caseorigincode=Origin&statecode=Status&statuscode=Status%20Reason&createdon=Created%20On&is_duration=Initial%20Estimation%20Duration&is_followupsupportteam=Follow%20Up%20Support%20Team&new_age=Age&prioritycode=Priority&new_duedate=Due%20Date&new_actualduration=Actual%20Duration&new_actualdurationdays=Actual%20Duration%20%28days%29&is_cr=CR%20%23
Development | Technical Issue | Functional Issue | New Request | System Administration | Reconciliation | Workflow | SFA | Retail & POS | Zatka | HR & Payroll | Deploy Package | Migration | Shopify | Fixed Assets | Budget | Training | R&D | PowerBi | Security
Pre-Sales | Support | Project | Change Request | Phone | Web | IoT | Internal Support
Active | Resolved | Cancelled
Not Started | In Progress | Requirement Gathering | Scope of Work | Solution Design | Estimation | In Process with Microsoft | Pending CR | Pending Functional | Pending Dev - Require Delivery Date | Pending Dev | Pending Testing | Pending Client Confirmation | Pending Customer | On Hold | Approved | Delivered To Client | Draft | Pending Internal Approval | Researching | Submitted | Requirement Gathering/Pending Briefing | Problem Solved | Information Provided | Cancelled | Merged | Rejected
Yes | No
High | Normal | Low